## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Creating Work Items List | 1 | 2 | Completed | 1 | Ömer Denizoğlu | 0 | 2 | Open Up Work Item List Template
Creating Iteration I Plan | 1 | 4 | Completed | 1 | Ömer Denizoğlu | 0 | 4 | Open Up Iteration Plan Template
Updating Vision Document | 2 | 2 | Completed | 1 | Mert Dervişoğulları- Irina Erofeeva | 0 | 2 | Open Up Vision Template
Creating Project Plan | 1 | 10 | Completed | 1 | Mert Dervişoğulları | 0 | 10 | Open Up Project Plan Template
Preparing System-Wide Requirements | 2 | 6 | Completed | 1 | Irina Erofeeva-Durali Alagöz | 0 | 6 | Open Up System-Wide Requirements Template
Defining All Use Cases Brief Format | 1 | 8 | Completed | 1 | Durali Alagöz- Irına Erofeeva-Ömer Denizoğlu | 0 | 10 | Open Up Use Case Specification Template
Defining Major Use Cases Fully Dressed Format | 1 | 10 | Completed | 1 | Durali Alagöz- Irına Erofeeva-Ömer Denizoğlu | 0 | 8 | Open Up Use Case Specification Template
Creating Glossary Document | 3 | 2 | Completed | 1 | Irına Erofeeva | 0 | 2 | All Project Artifacts
Creating Risk List | 2 | 4 | Completed | 1 | Durali Alagöz | 0 | 3 | Open Up Use Risk List Template
Creating Iteration II Plan | 2 | 4 | Completed | 1 | Ömer Denizoğlu | 0 | 4 | Open Up Iteration Plan Template
Preparing Development Environment | 1 | 4 | Completed | 2 | Durali Alagöz-Irina Erofeeva | 0 | 4 | System-Wide Requirement Specification
Detailing All Use Cases Fully Dressed Format | 1 | 10 | Completed | 2 | Mert Dervişoğulları-Irina Erofeeva-Durali Alagöz | 0 | 10 | Open Up Use Case Specification Template
Detailing System-Wide Requirements | 2 | 8 | Completed | 2 | Irina Erofeeva-Durali Alagöz | 0 | 8 | Open Up System-Wide Requirements Template
Developing the Architecture Notebook | 1 | 10 | Completed | 2 | Ömer Denizoğlu | 0 | 10 | Open Up Use Case Architecture Notebook Template
Creating Domain Model | 1 | 4 | Completed | 2.3 | Ömer Denizoğlu | 0 | 4 | Open Up Use Case Architecture Notebook Template
Creating Design Document | 1 | 8 | Completed | 2.3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 8 | Open Up Design Template
Creating Partial Executable | 1 | 10 | Completed | 2.3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 10 | Architecture Notebook, Fully Dressed Use Cases
Revising Iteration Plan I Artifacts | 2 | 4 | Completed | 2 | Mert Dervişoğulları | 0 | 4 | Iteration I Artifacts
Creating Test Cases for UC1, UC2 and UC3 | 1 | 4 | Completed | 2.3 | Mert Dervişoğulları | 0 | 4 | Open Up Test Case Template
Creating Test Cases for UC5, UC7 and UC9 | 1 | 4 | Completed | 4 | Mert Dervişoğulları | 0 | 4
Creating Test Script | 2 | 6 | Completed | 2.3 | Irina Erofeeva-Durali Alagöz | 0 | 6 | Open Up Test Script Template
Creating Test Log | 1 | 4 | Completed | 2.3 | Irina Erofeeva-Durali Alagöz | 0 | 4 | Open Up Test Log Template
Creating Iteration III Plan | 1 | 4 | Completed | 2 | Ömer Denizoğlu | 0 | 4 | Open Up Iteration Plan Template
Revising Iteration Plan II Artifacts | 2 | 4 | Completed | 3 | Mert Dervişoğulları | 0 | 4 | Iteration II Artifacts
Creating Iteration IV Plan | 1 | 4 | Completed | 3 | Mert Dervişoğulları | 0 | 4 | Open Up Iteration Plan Template
Creating Iteration V Plan | 1 | 4 | Completed | 4 | Mert Dervişoğulları | 0 | 4
Creating First Release | 1 | 12 | Not Started | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 12 | 0 | Architecture Notebook, Fully Dressed Use Cases
Creating Deployment Plan | 1 | 8 | Not Started | 4 | Mert Dervişoğulları- Durali Alagöz | 8 | 0 | Open Up Deployment
Revising Iteration Plan III Artifacts | 2 | 6 | Not Started | 4 | Mert Dervişoğulları | 6 | 0 | Iteration III Artifacts
Creating User Manual | 2 | 6 | Not Started | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva-Mert Dervişoğulları | 6 | 0 | Functional Requirements
Implement Fully Dressed Use Case 1 - Main Success Scenario | 1 | 8 | Completed | 2 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 8 | Use Case Model
Implement Fully Dressed Use Case 1 - Extensions | 1 | 4 | Completed | 2 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 4 | Use Case Model
Implement Fully Dressed Use Case 2 - Main Success Scenario | 1 | 7 | Completed | 2 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 7 | Use Case Model
Implement Fully Dressed Use Case 2 - Extensions | 1 | 3 | Completed | 3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 3 | Use Case Model
Implement Fully Dressed Use Case 3 - Main Success Scenario | 1 | 8 | Completed | 3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 8 | Use Case Model
Implement Fully Dressed Use Case 3 - Extensions | 1 | 4 | Completed | 3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 4 | Use Case Model
Implement Fully Dressed Use Case 4 - Main Success Scenario | 1 | 7 | In Progress | 5 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 7 | 0 | Use Case Model
Implement Fully Dressed Use Case 4 - Extensions | 1 | 3 | Not Started | 6 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 3 | 0 | Use Case Model
Implement Fully Dressed Use Case 5 - Main Success Scenario | 1 | 8 | Completed | 3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 8 | Use Case Model
Implement Fully Dressed Use Case 5 - Extensions | 1 | 4 | Completed | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 4 | Use Case Model
Implement Fully Dressed Use Case 6 - Main Success Scenario | 1 | 10 | Not Started | 7 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 10 | 0 | Use Case Model
Implement Fully Dressed Use Case 6 - Extensions | 1 | 4 | Not Started | 8 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 4 | 0 | Use Case Model
Implement Fully Dressed Use Case 7 - Main Success Scenario | 1 | 7 | Completed | 3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 7 | Use Case Model
Implement Fully Dressed Use Case 7 - Extensions | 1 | 3 | Completed | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 3 | Use Case Model
Implement Fully Dressed Use Case 8 - Main Success Scenario | 1 | 10 | Not Started | 9 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 10 | 0 | Use Case Model
Implement Fully Dressed Use Case 8 - Extensions | 1 | 4 | Not Started | 10 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 4 | 0 | Use Case Model
Implement Fully Dressed Use Case 9 - Main Success Scenario | 1 | 7 | Completed | 3 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 7 | Use Case Model
Implement Fully Dressed Use Case 9 - Extensions | 1 | 3 | Completed | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 3 | Use Case Model
Implement Fully Dressed Use Case 10 - Main Success Scenario | 1 | 10 | Not Started | 9 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 10 | 0 | Use Case Model
Implement Fully Dressed Use Case 10 - Extensions | 1 | 4 | Not Started | 9 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 4 | 0 | Use Case Model
Run Test Cases for Use Case 1 | 1 | 6 | Completed | 2 | Irina Erofeeva-Durali Alagöz | 0 | 6 | Prepared Test Cases
Run Test Cases for Use Case 2 | 1 | 4 | Completed | 3 | Irina Erofeeva-Durali Alagöz | 0 | 4 | Prepared Test Cases
Run Test Cases for Use Case 3 | 1 | 4 | Completed | 3 | Irina Erofeeva-Durali Alagöz | 0 | 4 | Prepared Test Cases
Run Test Cases for Use Case 4 | 1 | 6 | Not Started | 6 | Irina Erofeeva-Durali Alagöz | 6 | 0 | Prepared Test Cases
Run Test Cases for Use Case 5 | 1 | 4 | Completed | 4 | Irina Erofeeva-Durali Alagöz | 0 | 4 | Prepared Test Cases
Run Test Cases for Use Case 6 | 1 | 4 | Not Started | 5 | Irina Erofeeva-Durali Alagöz | 4 | 0 | Prepared Test Cases
Run Test Cases for Use Case 7 | 1 | 6 | Completed | 4 | Irina Erofeeva-Durali Alagöz | 0 | 6 | Prepared Test Cases
Run Test Cases for Use Case 8 | 1 | 4 | Not Started | 10 | Irina Erofeeva-Durali Alagöz | 4 | 0 | Prepared Test Cases
Run Test Cases for Use Case 9 | 1 | 4 | Completed | 4 | Irina Erofeeva-Durali Alagöz | 0 | 4 | Prepared Test Cases
Run Test Cases for Use Case 10 | 1 | 4 | Not Started | 9 | Irina Erofeeva-Durali Alagöz | 4 | 0 | Prepared Test Cases