# Hotel Reservation System

# Iteration Plan IV

# Revision History

| Date | Author | Description | Version |
| --- | --- | --- | --- |
| 30/05/2021 | Irina Erofeeva Ömer Denizoğlu Durali Alagöz M.Mert Dervişoğulları | First version | v 1.0 |

[Note: Text enclosed in square brackets and displayed in blue italics (style=InfoBlue) is included to provide guidance to the author and should be deleted before publishing the document.]

# 1.  Key milestones

| Milestone | Date |
| --- | --- |
| Iteration start | 03/06/2021 |
| Mitigate Risk 3 and 6 | 05/06/2021 |
| Revise Iteration Plan III Artifacts | 09/06/2021 |
| Implement Fully Dressed Use Case 5 Extensions | 16/06/2021 |
| Implement Fully Dressed Use Case 7 Extensions | 17/06/2021 |
| Implement Fully Dressed Use Case 9 Extensions | 19/06/2021 |
| Prepare Test Cases for Use Case 5, Use Case 7, Use Case 9 | 20/06/2021 |
| Run prepared Test Cases | 20/06/2021 |
| Iteration stop | 24/06/2021 |

# 2.  High-level objectives

- Fully implement Iteration IV Use Cases.

- Defining Risks, applying mitigation strategies related to iteration.

- Create and Run Test Cases

# 3.  Work Item assignments

Please see the Work Items List for Work Items to be addressed in this iteration.

| Name or key words of description | Priority | Size estimate (points) | State | Reference material | Target iteration | Assigned to (name) | Hours worked | Estimate of hours remaining |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implement Fully Dressed Use Case 5 - Extensions | 1 | 4 | In Progress | Use Case Model | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 4 |
| Implement Use Case 7 - Extensions | 1 | 3 | In Progress | Use Case Model | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 3 |
| Implement Use Case 9 - Extensions | 1 | 3 | In Progress | Use Case Model | 4 | Ömer Denizoğlu-Durali Alagöz-Irina Erofeeva | 0 | 3 |
| Creating Test Cases for UC5, UC7 and UC9 | 1 | 4 | In Progress | Open Up Test Case Template | 4 | Mert Dervişoğulları | 0 | 4 |
| Run Test Cases for UC5 | 1 | 4 | In Progress | Prepared Test Cases | 4 | Irina Erofeeva-Durali Alagöz | 0 | 4 |
| Run Test Cases for UC7 | 1 | 6 | In Progress | Prepared Test Cases | 4 | Irina Erofeeva-Durali Alagözı | 0 | 4 |
| Run Test Cases for UC9 | 1 | 4 | In Progress | Prepared Test Cases | 4 | Irina Erofeeva-Durali Alagöz | 0 | 4 |
| Creating Iteration V Plan | 1 | 4 | In Progress | Open Up Iteration Plan Template | 4 | Mert Dervişoğulları | 0 | 4 |

# 4.  Issues

| Issue | Status | Notes |
| --- | --- | --- |
| Finding an optimal development environment suitable for all team members. | Done | All team members have different operating systems and computers of different capacities, so we need to find tools that suit everyone. Optimal development environment is determined by team consensus. |

# 5.  Evaluation criteria

## 100% of Use Case 5, Use Case 7 and Use Case 9 are implemented and tested.

## Partial Executable must be updated.

## All of the related test cases must be passed.