## Risks
Hotel Reservation System Project Risk List v3.0
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2021-04-03 | Project Plan Failure | Project Plan will shift and late completion of the project | Schedule | 5 | 20% | 1 | Project Manager | Make internal reviews after each iteration and update project plan
2 | 2021-04-03 | Iteration Plan Failure | The planned work for the iteration will be done partially and rest will be left to the next iteration. | Schedule | 5 | 20% | 1 | Project Manager | Revise iterations' plan -> Done. Iteration Plan Failure has never occured due to the extra dedicated effort is performed by the team.
3 | 2021-04-09 | Requirements are misunderstood | HRS would not satisfy customer needs. | Business | 5 | 15% | 0.75 | Analyst | Using different elicitation techniques like prototyping focus group
4 | 2021-04-08 | Incompatibility with GUI and specific configurations on client machines. | Graphical user interfaces and custom configurations may not be compatible with client machines | Technical | 4 | 10% | 0.4 | Developer | Run the system on client machine before release 1. Adjust client machines or system based on the results.
5 | 2021-04-03 | Misunderstanding of the concepts of the Unified Process | The project team is relatively inexperienced with the Unified Process (UP) | Technical | 4 | 10% | 0.4 | Project Manager, Developer, Tester, Analyst | Schedule training sessions for the Unified Process. -> Done. The team has looked over Unified Process 3 times as a part of the team meeting activity. Establish 'process mentors' who can assist the team in understanding the process and the development activities. -> Undone. Despite of the other colleagues from several projects, particular process mentors are not assigned. Ensure all Design and Code is inspected. -> Done. Design and Code have been reviewed multiple times by all team members individually and collectively.
6 | 2021-04-09 | Developer may have difficulties with coding. | Developers may not have enough experienced in programming and face difficulties in constructing. | Technical | 3 | 10% | 0.3 | Developer | Select a familiar development libraries and infrastructure.
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0