# Hotel Reservation System

# Project Plan

# Revision History

| Date | Author | Description | Version |
| --- | --- | --- | --- |
| 12/04/2021 | Irina Erofeeva Ömer Denizoğlu Durali Alagöz M.Mert Dervişoğulları | First version | v 1.0 |
| 17/04/2021 | Irina Erofeeva Ömer Denizoğlu Durali Alagöz M.Mert Dervişoğulları | Second version | v 1.1 |
| 03/05/2021 | Irina Erofeeva Ömer Denizoğlu Durali Alagöz M.Mert Dervişoğulları | Third version | v 1.2 |

# Introduction

This project plan consists of roles during the project, statement of practices and measurements and detailed schedule including particular project milestones in terms of requested achievements.

# Project organization

The Hotel Management System Project will be developed by the team members whose roles are also stated as follows.

| Team Member Name | Primary Role | Secondary Role |
| --- | --- | --- |
| Irina Erofeeva | Software Developer | Software Tester |
| Ömer Denizoğlu | Software Architect | Software Developer |
| Durali Alagöz | Software Developer | Software Tester |
| M.Mert Dervişoğulları | Project Manager | Analyst |

Furthermore, all the team members actively participate in quality assurance activities such as reviewing project documents and support other projects in requested quality assurance activities. In addition to current team members, additional team members will be determined as the independent quality team who are members of other projects.

# Project practices and measurements

Unified Process Iterative Development software development methodology is going to be followed during the project. In order to track progress of the project, Velocity is tracked and a Burndown Chart of the related iteration shall be reported at the end of each iteration to track the trend of the project. The estimated velocity for each task shall be determined by the team and the target velocity is not remaining below that estimation.

# Project milestones and objectives

| Iteration | Primary objectives (risks and use case scenarios) | Scheduled start or milestone | Target velocity |
| --- | --- | --- | --- |
| I1(iteration#1) | Objectives - Finalize Vision Document - Prepare Work Items List - Prepare Iteration I and II Plans - Prepare System-Wide Requirements - Prepare Glossary Document - Prepare Risk List - Prepare high-level use cases(i.e Brief Format) - Prepare “Use Case 1(UC1): Manage User Account” in fully dressed format - Prepare “Use Case 2(UC2): Manage Reservation of Room” in fully dressed format | 01.04.2021-15.04.2021 | 60 |
| E1(iteration#2) | Objectives - Mitigate Risk 5 - Prepare Development Environment - Prepare UC3 to UC8 in fully dressed format - Implement UC1, All Scenarios - Implement UC2, Main Success Scenario - Prepare Design and Architecture Notebook - Prepare Test Cases for UC1 - Run prepared Test cases. - Write Initial version of Iteration III Plan | 15.04.2021-06.05.2021 | 76 |
| E2(iteration#3) | Objectives - Mitigate Risk 2 - Implement UC2, Extensions - Implement UC3, All Scenarios - Implement UC5, Main Success Scenario - Implement UC7, Main Success Scenario - Implement UC9, Main Success Scenario - Prepare Design and Architecture Notebook - Prepare Test Cases for UC2, UC3 - Run prepared Test cases. | 06.05.2021-03.06.2021 | 80 |
| C1(iteration#4) | Objectives - Mitigate Risk 3, 6 - Implement UC5, Extensions - Implement UC7, Extensions - Implement UC9, Extensions - Prepare Test Cases for UC5, UC7, UC9 - Run prepared Test cases. | 03.06.2021-24.06.2021 | 80 |
| C2(iteration#5) | Objectives - Mitigate Risk 4 - Implement UC4, Main Success Scenario | 24.06.2021-15.07.2021 | 80 |
| C3(iteration#6) | - Implement UC4, Extensions - Prepare Test Cases for UC4 - Run prepared Test cases | 15.07.2021-05.08.2021 | 80 |
| C4(iteration#7) | - Implement UC6, Main Success Scenario - Run prepared Test cases | 05.08.2021 - 26.08.2021 | 80 |
| C5(iteration#8) | - Implement UC6, Extensions - Prepare Test Cases for UC6 - Run prepared Test cases | 26.08.2021 - 16.09.2021 | 80 |
| C6(iteration#9) | - Implement UC8, Main Success Scenario - Run prepared Test cases | 16.09.2021 - 07.10.2021 | 80 |
| C7(iteration#10) | - Implement UC8, Extensions - Prepare Test Cases for UC8 - Run prepared Test cases | 07.10.2021 - 28.10.2021 | 80 |

# Deployment

Production will be on Java/JDK. All deployments will be on Java, so a special deployment tool is not required. Information about hardware is defined in the System-wide Requirement Specifications Document.

# Lessons learned

Size estimate should not be calculated as an hour but in points.

In each project document there must be a revision history.